Project Plan & Risk Management Document

Household Appliances Rental Management System with AI Integration

Version 1.0  |  2026-08-04

# Table of Contents

# Part A: Project Plan

## A.1 Development Methodology

The project follows a phased build order (documented in TASK_LIST.md) rather than a strict single-pass waterfall: the core CRUD system is built and stabilized first (Phases 0-4), and the three AI modules are layered on afterward (Phase 5), since they depend on the core data (bookings) existing first. This is a pragmatic adaptation of the Classical Waterfall Model used in the reference House Rental Management System project, modified to de-risk the AI components by building them last, once real usage data patterns are understood.

## A.2 Phase Breakdown and Estimated Timeline

| Phase | Deliverable | Est. Duration |
| --- | --- | --- |
| Phase 0 | Project scaffolding (Django + React + MongoDB wired up) | Week 1 |
| Phase 1 | Authentication (JWT, 3 roles) | Week 2 |
| Phase 2 | Appliance catalog CRUD + search/filter | Week 3-4 |
| Phase 3 | Booking workflow (request/approve/return) | Week 5 |
| Phase 4 | Admin panel | Week 6 |
| Phase 5a | Recommendation engine (content-based + collaborative) | Week 7-8 |
| Phase 5b | Demand forecasting / BI dashboard | Week 9 |
| Phase 5c | Churn prediction module | Week 10 |
| Phase 6 | Polish, testing, documentation | Week 11 |

This mirrors the 11-week timeline used in the reference House Rental Management System project's Gantt chart, adapted to include the three AI phases in place of generic 'coding and testing' time.

## A.3 Resources

- Development environment: local machine running Python 3.11+, Node 18+, MongoDB (local or Atlas free tier)

- Training data: three Kaggle datasets (churn, demand forecasting, recommendations) identified in PROJECT_BRIEF.md

- Tooling: Antigravity (agentic IDE) for implementation, used against a pre-written specification

## A.4 Milestones

- M1 — End of Phase 0: application skeleton runs end-to-end (empty pages, but full stack connected)

- M2 — End of Phase 4: core rental system fully functional without any AI features

- M3 — End of Phase 5: all three AI modules trained, evaluated, and exposed via API

- M4 — End of Phase 6: system demo-ready with documentation

# Part B: Risk Management

## B.1 Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Kaggle datasets don't map cleanly to appliance categories | Medium | Medium | Document a manual category-relabeling step; fall back to synthetic data generation (pandas + Faker) if remapping proves too lossy |
| Collaborative filtering has too little interaction data to be meaningful early on | High | Low | Content-based filtering is the guaranteed fallback (FR-5.3); collaborative filtering is explicitly a secondary enhancement, not a blocker |
| MongoDB + Django ORM mismatch causes integration friction (Django assumes SQL) | Medium | Medium | MongoEngine chosen specifically to minimize this; avoid Django features that assume a relational ORM (e.g. built-in admin without adaptation) |
| Antigravity agent silently deviates from the agreed architecture | Medium | Medium | Locked-in specs in /specs, explicit "do not deviate, flag instead" instruction, phase-by-phase review before continuing |
| Churn model accuracy is poor due to small/synthetic dataset | Medium | Low | Report metrics honestly (accuracy/precision/recall/F1) as part of FR-7.4; a modest but honestly-reported result is acceptable for an academic project |
| Timeline slips due to unfamiliarity with Django + MongoEngine + ML stack simultaneously | High | Medium | Core rental app (Phases 0-4) intentionally has zero ML dependency, so a partial project is still a working, demonstrable deliverable |
| Scope creep (adding features beyond the three defined AI modules) | Medium | Medium | PROJECT_BRIEF.md explicitly lists what NOT to change without going back to the architect |

## B.2 Contingency Notes

If a phase is at risk of running over time, the core rental system (Phases 0-4) takes priority over all three AI modules — a working non-AI rental platform is a legitimate fallback deliverable, whereas an AI module with no underlying booking data to work from is not functional on its own.